## Reduce number of complain
Data input : C - CID - CRM - Resolution Lead Time on Customer Complain | [9 empty] | Legend | Recommendations
Target -80% per month Released (UAT) Issues and additional If Major (within 20 days),If Minor (within 5 days)
Financial Year | 2023/2024 |  |  |  | 2024/2025 |  |  |  |  | Calculated KPI Data (Do not change)
Month | Total No. of Complaint | Actual resolution no. of complaint within Leadtime | Achievement |  | Total No. of Complaint | Actual resolution no. of complaint within Leadtime | Achievement |  |  | Your data (White Cells) | Please fill in your data in blank white cells
[10 empty] | 1 | Turnover is conforming with established target (well done and keep improvement)
Apr |  |  |  | 50% | 24 | 24 | 100% | 80% |  | 0.5 | Results are under the established target, but within a tolerance interval. They need to be analyzed and monitored
May |  |  |  | 50% | 17 | 17 | 100% | 80% |  | 0 | Turnover exceeds target limit (Please investigate and take urgent actions)
Jun |  |  |  | 50% | 19 | 19 | 100% | 80% | [5 empty] | Trend
Jul |  |  |  | 50% |  |  |  | 80% |  | 2024/2025 |  | J |  | #VALUE!
Aug |  |  |  | 50% |  |  |  | 80%
Sep |  |  |  | 50% |  |  |  | 80%
Oct |  |  |  | 50% |  |  |  | 80%
Nov |  |  |  | 50% |  |  |  | 80% |  | Action Plan
Dec |  |  |  | 50% |  |  |  | 80% |  | 1-……………………………………………………………………………………………..
Jan |  |  |  | 50% |  |  |  | 80% |  | 2-……………………………………………………………………………………………..
Feb |  |  |  | 50% |  |  |  | 80% |  | 3-……………………………………………………………………………………………..
Mar |  |  |  | 50% |  |  |  | 80% |  | 4-……………………………………………………………………………………………..
YTD |  |  |  |  | 60 | 60 |  |  |  | 5-……………………………………………………………………………………………..
Average |  |  |  |  | 20 | 20 |  |  |  | 6-……………………………………………………………………………………………..
Performance |  |  |  |  | 100% |  |  |  |  | 7-……………………………………………………………………………………………..
KPI Analysis
KPI Definition
BSC Perspective | KPI | Process | Frequency | Definition |  |  |  |  | Objective |  |  | Numerator | Denominator
Customer | Resolution Lead Time on Customer Complain | TBD | Monthly | [8 empty] | Total No. of Complaint | Actual resolution no. of complaint within Leadtime
KPI Profile
Direction | Unit
Maximize | Percentage

## Apr2024
No. | Project Name | Released Version | Module | Submodule | Funtions | Issues Description | BU/BR Name | Raised By | Priority (Impact) | Months | Issue Types | Issue Date | Status | CID Received Date | CID Delivered Date | Duration | Resolution by CID | Major/Minor | Reason for Major | Remark
1 | Mechanic Activity (AFS) | UAT | Sale Order |  | Confirm Sale Order | Mobile ဘက်တွင် sale order confirm နှိပ်လို့ရရန်။ | AFS | Cherry Soe | Low | April | Additional | 2024-02-22 | Pass | 2024-02-22 | 2024-04-05 | 21 |  | Minor |  | 25.Feb.2024 is holiday. 2,3,10,16,17,24,27,30,31.Mar.2024 are holidays. 7,13,14,15,16,17,18,10,20,21,27,28.Apr.2024 are holidays.
2 | Mechanic Activity (AFS) | UAT | Service Report |  |  | Report တွင် In progress မှလွဲ၍ ကျန် status ( Finished, Job Cancel, Waiting Customer, Waiting load and Waiting Parts) များဆိုပါက assign ပြန်ချလို့ရရန်။ | AFS | Cherry Soe | Low | April | System Upgrade | 2024-03-15 | Pass | 2024-03-15 | 2024-04-05 | 3 |  | Minor |  | 16,17,24,27,30,31.Mar.2024 are holidays. 7,13,14,15,16,17,18,10,20,21,27,28.Apr.2024 are holidays.
3 | Mechanic Activity (AFS) | UAT | Part Recommendation |  | Edit Part Recommendation Approve by Leader | Part recommendation မှာ approved ပေးမဲ့ leader ကို view only မဖြစ်ရ edit ထည့်ပေးရန် Qty ပါပြင်စေချင်တာ။ | AFS | Cherry Soe | Low | April | Additional | 2024-02-14 | Pass | 2024-02-14 | 2024-04-05 | 27 |  | Minor |  | 18,19,25.Feb.2024 is holiday. 2,3,10,16,17,24,27,30,31.Mar.2024 are holidays. 7,13,14,15,16,17,18,10,20,21,27,28.Apr.2024 are holidays.
4 | Mechanic Activity (AFS) | UAT | Mechanic Activity |  | Search Job | Mechanic activity တွင် Job Accepted/ Rejected များကို search တွင်ရှာလျှင် Status နဲ့လည်းရှာ လို့ရချင်ပါသည်။ လက်ရှိတွင် Job order no နှင့်ရှာလို့ရပါသည်။ | AFS | Cherry Soe | Low | April | Additional | 2024-03-15 | Pass | 2024-03-15 | 2024-04-05 | 3 |  | Minor |  | 16,17,24,27,30,31.Mar.2024 are holidays. 7,13,14,15,16,17,18,10,20,21,27,28.Apr.2024 are holidays.
5 | Mechanic Activity (AFS) | UAT | User |  | Remove Req. Field | User တွင် NRC, Region, City, & Township etc Required Field ဖြုတ်ပေးပါရန်။ (Remove requierd fields( stages, township, NRC and mobile) if partner is only user). | AFS | Cherry Soe | Low | April | System Upgrade | 2024-03-25 | Pass | 2024-03-25 | 2024-04-05 | 11 |  | Minor |  | 30,31.Mar.2024 are holidays. 7,13,14,15,16,17,18,10,20,21,27,28.Apr.2024 are holidays.
6 | Mechanic Activity (AFS) | UAT | Job Order |  | Unassign Job after Job Finished | Job Finished ဆို Assign ပြန်ချလို့မရရန်။ | AFS | Cherry Soe | Low | April | System Upgrade | 2024-03-25 | Pass | 2024-03-25 | 2024-04-05 | 11 |  | Minor
7 | Mechanic Activity (AFS) | UAT | Job Order |  | Replace mechanic | Replacement Mechanic တွင် From တွင်ရွေးထားသော Mechanic ကို To တွင်ပြန်ရွေးလို့ရရန်။ | AFS | Cherry Soe | Low | April | System Upgrade | 2024-03-25 | Pass | 2024-03-25 | 2024-04-05 | 11 |  | Minor
8 | Mechanic Activity (AFS) | UAT | Report |  | Revenue Achievement Report | RV date နေရာတွင် RV no ကျနေ | AFS | Cherry Soe | Low | April | System Issue | 2024-04-10 | Pass | 2024-04-11 | 2024-04-24 | 4 |  | Minor |  | 13,14,15,16,17,18,19,20,21.Apr.2024 are holidays.
9 | EDMS | UAT | EDMS | EDMS | Download Master Form | BU အတွက် Member of, Relentless Pursuit Of Excellence ပါတဲ့ UMG Logo ပြောင်းပေးရန်။ | CHLD | Shwe Yi Thoon Phyo | Low | April | Change | 2024-03-25 | Pass | 2024-03-26 | 2024-04-01 | 3 |  | Minor |  | 27,30,31.Mar.2024 are holidays
10 | EDMS | UAT | EDMS | EDMS | FPD, SOP, FORM, EKD, RCL | Document No. အတွက် revise no. ပေါ်တဲ့ အခါ ၂ လုံးစာပဲ ("001" ကို "01" လို့ပဲ) ဖော်ပေးရန် | CHLD | Shwe Yi Thoon Phyo | Low | April | Change | 2024-03-25 | Pass | 2024-03-26 | 2024-04-03 | 5 |  | Major | Need to change all form | 27,30,31.Mar.2024 are holidays
11 | EDMS | UAT | EDMS | EDMS | Record List | Store ကို Storage လို့ ပြင်ပေးပါရန်။ | CHLD | Shwe Yi Thoon Phyo | Low | April | Additional | 2024-03-25 | Pass | 2024-03-26 | 2024-04-01 | 3 |  | Minor |  | 27,30,31.Mar.2024 are holidays
12 | EDMS | UAT | EDMS | EDMS | Record List | View side တွင် Business Name ဖော်ပေးရန်။ | CHLD | Shwe Yi Thoon Phyo | Low | April | Additional | 2024-03-25 | Pass | 2024-03-26 | 2024-04-01 | 3 |  | Minor |  | 27,30,31.Mar.2024 are holidays
13 | EDMS | UAT | EDMS | EDMS | EKD | EKD တွင် Remark အား requirement field အားဖြုတ်ပေးပါရန် | CHLD | Shwe Yi Thoon Phyo | Low | April | Change | 2024-03-25 | Pass | 2024-03-26 | 2024-04-01 | 3 |  | Minor |  | 27,30,31.Mar.2024 are holidays
14 | EDMS | UAT | EDMS | EDMS | Record List | Record List တွင် Title Field name အား ပြောင်းပေးရန် | CHLD | Shwe Yi Thoon Phyo | Low | April | Additional | 2024-03-25 | Pass | 2024-03-26 | 2024-04-01 | 3 |  | Minor |  | 27,30,31.Mar.2024 are holidays
15 | EDMS | UAT | EDMS | EDMS | Download Master Form | Form Download တွင် All form ကို download ချလို့ရနေတာအား Related BU/BR/DIV only သာ ကျပေးရန် | CHLD | Shwe Yi Thoon Phyo | Low | April | Additional | 2024-03-25 | Pass | 2024-03-26 | 2024-04-03 | 5 |  | Major | Changed access right process | 27,30,31.Mar.2024 are holidays
16 | EDMS | UAT | EDMS | EDMS | All EDMS | Project Leader, SND Head, GM/AGM, COO Approve ပေးမယ့်နေရာမှာ သူရွေးထားတဲ့ user တွေကပဲ approve ပေးလိုရအောင် ပြင်ချင်ပါတယ် | CHLD | Shwe Yi Thoon Phyo | Low | April | System Issue | 2024-03-25 | Pass | 2024-03-26 | 2024-04-01 | 3 |  | Major | Changed access right process | 27,30,31.Mar.2024 are holidays
17 | EDMS | UAT | EDMS | EDMS | Download Master Form | Download Master Form လို့ပြောင်းပေးရန် | CHLD | Shwe Yi Thoon Phyo | Low | April | Additional | 2024-03-25 | Pass | 2024-03-26 | 2024-04-01 | 3 |  | Minor |  | 27,30,31.Mar.2024 are holidays
18 | EDMS | UAT | EDMS | EDMS | EKD, RCL | DH create လုပ်ထားသော အစောင်ကို Dept တူ user က ပြင်လိုရနေတယ်ပါသည် ပိတ်ပေးရန် ((EKD, RCL) (DH,GM/AGM - open, User, SND Head, Project Leader, COO - closed)Edit ကော Revise button ကောပိတ်မယ်) | CHLD | Shwe Yi Thoon Phyo | Low | April | System Issue | 2024-03-25 | Pass | 2024-03-26 | 2024-04-01 | 3 |  | Major | Changed access right process | 27,30,31.Mar.2024 are holidays
19 | EDMS | UAT | EDMS | EDMS | FORM | FORM မှာ SND Head က confirm မနှိပ်ခင် ‌သူ attached တွဲလိုက်တဲ့ word file ကို (convert to pdf)ဆိုတဲ့ action လေး ကို နှိပ်လိုက်ရင် pdf အနေနဲ့ ပြပေးပြီး အဆင်မပြေဘူးဆို သူတွဲထားတဲ့ word file attached ကို remove လုပ်ပြီး ပြန်တွဲပြီး pdf view ပြန်ကြည့်ပြီး ok မှ confirm ကို နှိပ်ချင်ပါတယ် | CHLD | Shwe Yi Thoon Phyo | Low | April | Additional | 2024-03-25 | Pass | 2024-03-26 | 2024-04-03 | 5 |  | Major | Changed FORM process | 27,30,31.Mar.2024 are holidays
20 | Spare Part Salesman | UAT | Salesman CRM | Salesman CRM | Monthly Way Plan , Daily Way Plan (Mobile) | Finical year က 2024-2025 ဖြစ်ရမှာကို 2023-2024 ဖြစ်နေလို့ စမ်းမရပါ | AFS | Cherry Soe | Low | April | System Issue | 2024-04-06 | Pass | 2024-04-08 | 2024-04-11 | 3 |  | Minor
21 | Spare Part Salesman | UAT | Salesman CRM | Salesman CRM | Approval | Mobile ကနေ approved ပေးလို့မရပါ | AFS | Cherry Soe | Low | April | System Issue | 2024-04-06 | Pass | 2024-04-08 | 2024-04-11 | 3 |  | Minor
22 | Spare Part Salesman | UAT | Salesman CRM | Salesman CRM | Call | Call activities တွင် Daily way plan မှာ target ချခဲ့တဲ့ call customer ပဲ မပေါ်ပဲ contact ချိတ်ထားတာ all ကျနေလို့ပါ | AFS | Cherry Soe | Low | April | System Issue | 2024-04-06 | Pass | 2024-04-08 | 2024-04-11 | 3 |  | Minor
23 | Spare Part Salesman | UAT | Salesman CRM | Salesman CRM | visit | Way plan မှာ တင်ခဲ့တဲ့ visit customer ပဲ ကျပေးရန် call တေပါ ကျမနေရ | AFS | Cherry Soe | Low | April | System Issue | 2024-04-06 | Pass | 2024-04-08 | 2024-04-11 | 3 |  | Minor
24 | Spare Part Salesman | UAT | Salesman CRM | Salesman CRM | Monthly Way Plan ,approval | Monthly way plan ကို Backend ကနေတင်ပီး approve ပေးလိုက်ရင် Finical Year ပြန်ပြန် change သွားတဲ့အတွက် Daily Way Plan မှာမပေါ်ပါ | AFS | Cherry Soe | Low | April | System Issue | 2024-04-06 | Pass | 2024-04-08 | 2024-04-11 | 3 |  | Minor
25 | Spare Part Salesman | UAT | Salesman CRM | Salesman CRM | Call | Andriod version စစ်ပေးရန် (ဖုန်းတိုင်း call function သုံးမရပါ ) | AFS | Cherry Soe | Low | April | System Issue | 2024-04-06 | Pass | 2024-04-08 | 2024-04-30 | 11 |  | Major | Checked all android version | 13,14,15,16,17,18,19,20,21,27,28.April.2024 are holidays
26 | Spare Part Salesman | UAT | Salesman CRM | Salesman CRM | Call | Call form မှာ call feedback ဖြစ်ရမှာ name ပြင်ရန် | AFS | Cherry Soe | Low | April | System Issue | 2024-04-06 | Pass | 2024-04-08 | 2024-04-11 | 3 |  | Minor
27 | Spare Part Salesman | UAT | Salesman CRM | Salesman CRM | Call | Call form ဖြည့်ပြီး save ရင် call code က 2 ခုထွက်နေပါတယ် Backend မှာရော code တစ်ခြက draft ဖြစ်ပြီး code 2 ခု save သွားပါသည် | AFS | Cherry Soe | Low | April | System Issue | 2024-04-06 | Pass | 2024-04-08 | 2024-04-11 | 3 |  | Minor
28 | Spare Part Salesman | UAT | Salesman CRM | Salesman CRM | Inquire & prospect | Map ကို street လောက်တော့ ပေါ်ပေးရန် report မှာ ဆွဲထုတ်ရင် Lat ,lon နဲ့ပဲ အဆင်မပြေလို့ပါ | AFS | Cherry Soe | Low | April | Change | 2024-04-06 | Pass | 2024-04-08 | 2024-04-11 | 3 |  | Minor
29 | TIS | UAT | HRD Assessment |  | Orientation Evaulation | HRD Assessment >> Orientation Evaluation ( Criteria >> Orientation Assessment) - orientation assessment scores needs to be shown with weight result just like behavior assessment below. | CHLD | HRD Team | Low | April | Change | 2024-04-04 | Pass | 2024-04-05 | 2024-04-24 | 9 |  | Minor |  | 7,13,14,15,16,17,18,19,20,21.April.2024 are holidays.
30 | TIS | UAT | Reporting |  | Training Database Report | Want to multi Select for Employee type /Module | CHLD | Training Team | Low | April | Change | 2024-04-02 | Pass | 2024-04-03 | 2024-04-08 | 4 |  | Minor |  | 7.April.2024 is holiday.
31 | TIS | UAT | Increment Management |  | Approval | In increment data, I want to Know who gave it to Approve | CHLD | Training Team | Low | April | Additional | 2024-04-02 | Pass | 2024-04-03 | 2024-04-08 | 4 |  | Minor |  | 7.April.2024 is holiday.
32 | TIS | UAT | Reporting |  | Attendance List Report | In the Attendance List Report, who attended which module ,From Date ,to date ,does not appear in the list view | CHLD | Training Team | Low | April | Change | 2024-04-02 | Pass | 2024-04-03 | 2024-04-24 | 11 |  | Minor |  | 7,13,14,15,16,17,18,19,20,21.April.2024 are holidays.

## May2024
No. | Project Name | Released Version | Module | Submodule | Funtions | Issues Description | BU/BR Name | Raised By | Priority (Impact) | Months | Issue Types | Issue Date | Status | CID Received Date | CID Delivered Date | Duration | Resolution by CID | Major/Minor | Reason for Major | Remark
1 | Mechanic Activity (AFS) | v 1.4.0 | Job Order |  | Assigned job | Assign job မှာ တစ်ယောက်ထဲရွေးထားပေးမဲ့ backend မှာ 2 ယောက်ပေါ် , Leader ကို member မှာ assigned ပြန်ချလို့ရနေ။ | AFS | Cherry Soe | Low | MAY | System Upgrade | 2024-04-11 | Pass | 2024-04-11 | 2024-05-17 | 22 |  | Minor |  | 13,14,15,16,17,18,19,20,21,27,28.April.2024, 5,10,11.May.2024 are holidays.
2 | Mechanic Activity (AFS) | v 1.4.0 | Share Job |  | Share job | Share job approved confirm မဖြစ်ပဲ e learnig မှာမပေါ်ရ | AFS | Cherry Soe | Low | MAY | User Issue | 2024-04-11 | Pass | 2024-04-11 | 2024-05-17 | 22 |  | Minor |  | 13,14,15,16,17,18,19,20,21,27,28.April.2024, 5,10,11.May.2024 are holidays.
3 | Mechanic Activity (AFS) | v 1.4.0 | Job Order |  | Job accept | leader accept လုပ်မှသာ member mechanic တွေမှာပေါ်နေလို assigned ချထဲက ပေါ်ပေးရန် accept သာလုပ်ခွင့်မရှိရမှာ။ | AFS | Cherry Soe | Low | MAY | System Upgrade | 2024-04-11 | Pass | 2024-04-11 | 2024-05-17 | 22 |  | Minor |  | 13,14,15,16,17,18,19,20,21,27,28.April.2024, 5,10,11.May.2024 are holidays.
4 | Mechanic Activity (AFS) | v 1.4.0 | Job Order |  | Call to customer | Waiting customer ဆို job activities တွေဝင်လို့ရနေ Call to customer မှာwaiting ရွေးလိုက်ရင် unscheuled ပြန်ဖြစ်ရန် | AFS | Cherry Soe | Low | MAY | Additional | 2024-04-11 | Pass | 2024-04-11 | 2024-05-17 | 22 |  | Minor |  | 13,14,15,16,17,18,19,20,21,27,28.April.2024, 5,10,11.May.2024 are holidays.
5 | Mechanic Activity (AFS) | v 1.4.0 | Imporvement Assessment |  | Improvement assessment | Current date ပဲထား၇န် back date များ disable လုပ်ထားရန်, day by day job assign မရှိတဲ့သူပဲ form ဖြည့်လို့ရစေရန် , ရေးပြီးသားလူကိုကျတော့ assignd ချလို့ရရမယ် | AFS | Cherry Soe | Low | MAY | Additional | 2024-04-11 | Pass | 2024-04-11 | 2024-05-17 | 22 |  | Minor |  | 13,14,15,16,17,18,19,20,21,27,28.April.2024, 5,10,11.May.2024 are holidays.
6 | Mechanic Activity (AFS) | v 1.4.0 | Share Job |  | Job share | BU head က BU က own job ကို share လို့မရပါ. BU head မှလည်း share job form ဖြည့်ပြီး Job share ကိုယ်တိုင်လုပ်လို့ရရန်။ | AFS | Cherry Soe | Low | MAY | Additional | 2024-04-11 | Pass | 2024-04-11 | 2024-05-17 | 22 |  | Minor |  | 13,14,15,16,17,18,19,20,21,27,28.April.2024, 5,10,11.May.2024 are holidays.
7 | Mechanic Activity (AFS) | v 1.4.0 | Evaluation Job |  | Evaluation | job evaluation မှာ နာမည်တူထပ်နေ | AFS | Cherry Soe | Low | MAY | System Upgrade | 2024-04-11 | Pass | 2024-04-11 | 2024-05-17 | 22 |  | Minor |  | 13,14,15,16,17,18,19,20,21,27,28.April.2024, 5,10,11.May.2024 are holidays.
8 | Mechanic Activity (AFS) | v 1.4.0 | Job Order |  | Part Recommendation | Approved or reject ကို ပြန်ဝင်ပြီး approved ပေးလို့ရနေတယ်။ Recommendation notification တွင် Approve or Reject လုပ်ပြီးပါက Approve or Reject ထပ်လုပ်လို့မရ‌အောင် ပြုလုပ်ထားပေးပါရန်။ | AFS | Cherry Soe | Low | MAY | Additional | 2024-04-11 | Pass | 2024-04-11 | 2024-05-17 | 22 |  | Minor |  | 13,14,15,16,17,18,19,20,21,27,28.April.2024, 5,10,11.May.2024 are holidays.
9 | Mechanic Activity (AFS) | v 1.4.0 | Job Order |  | Job assigned | Service head က job ပြိုင်ပြီး သွားရလို In progress ဖြစ်နေလဲ Service Head role ကို assign ပြန်ချလိုရရန်. | AFS | Cherry Soe | Low | MAY | Additional | 2024-04-11 | Pass | 2024-04-11 | 2024-05-17 | 22 |  | Minor |  | 13,14,15,16,17,18,19,20,21,27,28.April.2024, 5,10,11.May.2024 are holidays.
10 | Mechanic Activity (AFS) | v 1.4.0 | Job Order |  | Job assigned | ခွင့်ပြုထားသော Service Head မှလွဲ၍ တနေ့တာအတွက် Assign ချပြီးသား Mechanic အား Job assigned တွင် Disable လုပ်ပေးရန် | AFS | Cherry Soe | Low | MAY | System Upgrade | 2024-04-11 | Pass | 2024-04-11 | 2024-05-17 | 22 |  | Minor |  | 13,14,15,16,17,18,19,20,21,27,28.April.2024, 5,10,11.May.2024 are holidays.
11 | Mechanic Activity (AFS) | v 1.4.0 | Job Order |  | Reopen Job | Job Close ဖြစ်သွားပါကလည်း Super admin acc မှ Reopen Job လုပ်လို့ရရန်။ | AFS | Cherry Soe | Low | MAY | New | 2024-04-11 | Pass | 2024-04-11 | 2024-05-17 | 22 |  | Minor |  | 13,14,15,16,17,18,19,20,21,27,28.April.2024, 5,10,11.May.2024 are holidays.
12 | Mechanic Activity (AFS) | v 1.4.0 | MIO |  | MIO | Update & non-update and Active & In-active calculation | AFS | Cherry Soe | Low | MAY | Additional | 2024-04-11 | Pass | 2024-04-11 | 2024-05-17 | 22 |  | Minor |  | 13,14,15,16,17,18,19,20,21,27,28.April.2024, 5,10,11.May.2024 are holidays.
13 | Mechanic Activity (AFS) | v 1.4.0 | Job Order |  | Part recommendation | Required field for photo attached in part recommendation. | AFS | Cherry Soe | Low | MAY | Additional | 2024-04-11 | Pass | 2024-04-11 | 2024-05-17 | 22 |  | Minor |  | 13,14,15,16,17,18,19,20,21,27,28.April.2024, 5,10,11.May.2024 are holidays.
14 | Mechanic Activity (AFS) | v 1.4.0 | Job Order |  | Overall checking | Required field for photo attached in overall checking | AFS | Cherry Soe | Low | MAY | Additional | 2024-04-11 | Pass | 2024-04-11 | 2024-05-17 | 22 |  | Minor |  | 13,14,15,16,17,18,19,20,21,27,28.April.2024, 5,10,11.May.2024 are holidays.
15 | Mechanic Activity (AFS) | v 1.4.0 | Job Order |  |  | Required field for status, service report, checking photo, customer name, finished date, customer sign. | AFS | Cherry Soe | Low | MAY | Additional | 2024-04-11 | Pass | 2024-04-11 | 2024-05-17 | 22 |  | Minor |  | 13,14,15,16,17,18,19,20,21,27,28.April.2024, 5,10,11.May.2024 are holidays.
16 | Mechanic Activity (AFS) | v 1.4.0 | Job Order |  | Part recommendation | Required field for checking image in Part usage. | AFS | Cherry Soe | Low | MAY | Additional | 2024-04-11 | Pass | 2024-04-11 | 2024-05-17 | 22 |  | Minor |  | 13,14,15,16,17,18,19,20,21,27,28.April.2024, 5,10,11.May.2024 are holidays.
17 | Mechanic Activity (AFS) | v 1.4.0 | Job Order |  | Draft Invoice | Required field for customer sign in Draft invocie. | AFS | Cherry Soe | Low | MAY | Additional | 2024-04-11 | Pass | 2024-04-11 | 2024-05-17 | 22 |  | Minor |  | 13,14,15,16,17,18,19,20,21,27,28.April.2024, 5,10,11.May.2024 are holidays.
18 | Mechanic Activity (AFS) | v 1.4.0 | Job Order |  | Service Report | Required field for date, theme(title),Objective, report, image. | AFS | Cherry Soe | Low | MAY | Additional | 2024-05-24 | Pass | 2024-05-24 | 2024-05-31 | 5 |  | Minor |  | 25,26.May.2024 are holidays.
19 | Mechanic Activity (AFS) | v 1.4.1 | Job Order |  | Job Order | Job order မှာ machine name blank ပြနေလို့ပါ inventory မှာ product ဆောက်တုန်းက ပါပါတယ် | AFS | Cherry Soe | Low | MAY | System Issue | 2024-05-24 | Pass | 2024-05-24 | 2024-05-31 | 5 |  | Minor |  | 25,26.May.2024 are holidays.
20 | Mechanic Activity (AFS) | v 1.4.1 | Job Order |  | Invoice | Invoice မှာ ‌admin ကိုလဲ ဖွင့်ခွင့်ပေးရန် | AFS | Cherry Soe | Low | MAY | System Issue | 2024-05-24 | Pass | 2024-05-24 | 2024-05-31 | 5 |  | Minor |  | 25,26.May.2024 are holidays.
21 | Mechanic Activity (AFS) | v 1.4.1 | Reporting |  | Utilization Report | Utilization report မှာ working hours တွေ မှားနေ | AFS | Cherry Soe | Low | MAY | System Issue | 2024-05-24 | Pass | 2024-05-24 | 2024-05-31 | 5 |  | Minor |  | 25,26.May.2024 are holidays.
22 | Mechanic Activity (AFS) | v 1.4.1 | Job Order |  | Reopen | Repoen ပြန်ဖွင့်ရင် mobile မှာ status မှာ Null ပြနေလို့ ပြင်ပေးပါရန် | AFS | Cherry Soe | Low | MAY | System Issue | 2024-05-24 | Pass | 2024-05-24 | 2024-05-31 | 5 |  | Minor |  | 25,26.May.2024 are holidays.
23 | Mechanic Activity (AFS) | v 1.4.1 | Job Order |  | Evaluation Job | Today job အကုန်မှာ evaluation တစ်ခုမှမပေးရသေးပဲ ပေးပြီးသားတေလိုပြနေလိုပါ | AFS | Cherry Soe | Low | MAY | System Issue | 2024-05-24 | Pass | 2024-05-24 | 2024-05-31 | 5 |  | Minor |  | 25,26.May.2024 are holidays.
24 | Mechanic Activity (AFS) | v 1.4.1 | Job Order |  | Overall checking | Overall checking မှာ Km နဲ့ Hr ကို require ဖြုတ်ရန် | AFS | Cherry Soe | Low | MAY | Additional | 2024-05-24 | Pass | 2024-05-24 | 2024-05-31 | 5 |  | Minor |  | 25,26.May.2024 are holidays.
25 | Mechanic Activity (AFS) | v 1.4.1 | Job Order |  | Quotation | Quotation မှာ service ကို dafault ထားပေးရန် | AFS | Cherry Soe | Low | MAY | System Upgrade | 2024-05-24 | Pass | 2024-05-24 | 2024-05-31 | 5 |  | Minor |  | 25,26.May.2024 are holidays.
26 | Mechanic Activity (AFS) | v 1.4.1 | Job Order |  | Quotation | Quotation မှာ service item ကို တစ်ခုထဲပဲ ထည့်လို့ရနေ ၂ ခု ထည့်မိရင် draf invoice သုံးမရပါ (Service item = service charges , Travelling charges , additional charges ) | AFS | Cherry Soe | Low | MAY | System Issue | 2024-05-24 | Pass | 2024-05-24 | 2024-05-31 | 5 |  | Minor |  | 25,26.May.2024 are holidays.
27 | Customer App & Admin System (WFN) | v 2.3.1 | Accounting & Invoicing |  | Statement Report | Remark duplication in statement report | WFN | Theingi Naing Tun | Low | MAY | User Error | 2024-05-24 | Pass | 2024-05-24 | 2024-05-24 | 0 |  | Minor
28 | Customer App & Admin System (WFN) | v 2.3.1 | Accounting & Invoicing |  | Contract | WF/EEL-204/2024 ကို contract stage ကိုပြန်ချပေးရန်။ | WFN | Theingi Naing Tun | Low | MAY | User Error | 2024-05-21 | Pass | 2024-05-21 | 2024-05-21 | 0 |  | Minor
29 | Customer App & Admin System (WFN) | v 2.3.1 | Accounting & Invoicing |  | Contract | Duplicate contracts | WFN | Theingi Naing Tun | Low | MAY | System Issue | 2024-05-20 | Pass | 2024-05-20 | 2024-05-20 | 0 |  | Minor
30 | Customer App & Admin System (WFN) | v 2.3.1 | Document Apply |  |  | APP ID duplicating error | WFN | Thet Naung Soe | Low | MAY | System Issue | 2024-05-17 | Pass | 2024-05-17 | 2024-05-20 | 2 |  | Minor
31 | Customer App & Admin System (WFN) | v 2.3.1 | Loan Request |  |  | Disappear NRC in EEL Request | WFN | Thet Naung Soe | Low | MAY | System Issue | 2024-05-16 | Pass | 2024-05-16 | 2024-05-16 | 0 |  | Minor
32 | Customer App & Admin System (WFN) | v 2.3.1 | User Creation |  |  | User account creation | WFN | Theingi Naing Tun | Low | MAY | New | 2024-05-15 | Pass | 2024-05-15 | 2024-05-15 | 0 |  | Minor
33 | Customer App & Admin System (WFN) | v 2.3.1 | User Registration |  |  | OTP does not send in new user account creation | WFN | Thet Naung Soe | Low | MAY | User Error | 2024-05-14 | Pass | 2024-05-14 | 2024-05-14 | 0 |  | Minor
34 | Customer App & Admin System (WFN) | v 2.3.1 | Survey result |  |  | Can not submit credit assessment survey result in SMEL | WFN | Pyae Sone | Low | MAY | User Error | 2024-05-04 | Pass | 2024-05-04 | 2024-05-06 | 1 |  | Minor |  | 5.May.2024 is holiday.

## Jun2024
No. | Project Name | Released Version | Module | Submodule | Funtions | Issues Description | BU/BR Name | Raised By | Priority (Impact) | Months | Issue Types | Issue Date | Status | CID Received Date | CID Delivered Date | Duration | Resolution by CID | Major/Minor | Reason for Major | Remark
1 | AMS | UAT | Fleet |  | Reporting | Extra Fuel Amount Report တွင် Trip Gallon ထဲတွင် လရောပြီး ပါနေတယ်. Fuel extra rreport တွင် trip gallon သည် 6 လပိုင်းတွင်ရှိသည့် trip gallon သာလျှင် မပေါ်ပဲ ကျန်လများ၏ gallon များပါနေပြီးမှားနေပါသည် | CAM | Vehicle Team | Low | JUNE | System Upgrade | 2024-06-14 | Pass | 2024-06-19 | 2024-06-26 | 5 | Su Myat Mon | Minor |  | 20,21 is holiday
2 | AMS | UAT | Fleet |  | Reporting | Vehicle Exist Permit Report တွင် Mile မပါသေးပါ. | CAM | Vehicle Team | Low | JUNE | Outstanding | 2024-06-15 | Pass | 2024-06-19 | 2024-06-26 | 5 | Su Myat Mon | Minor |  | 20,21 is holiday
3 | EMS | UAT | User Edit Permission |  |  | User Edit Permission ပေးရာတွင် PIC Department & BU/BR/DIV ကျပေးရန်။ | CHLD | Thiri Sandar Htun |  | JUNE | Change | 2024-06-01 | Pass | 2024-06-03 | 2024-06-17 | 11 | Su Myat Mon | Minor |  | 8,9,16 is holiday
4 | EMS | UAT | Admin Role |  |  | Admin Role တွင် Plan Create Permission မပေးထားဘူးဖြစ်နေပါသည်။ သို့သော် Admin Role မှ Plan Create တော့ လုပ်၍ရနေပါသည်။ | CHLD | Thiri Sandar Htun |  | JUNE | System Upgrade | 2024-06-01 | Pass | 2024-06-03 | 2024-06-17 | 11 | Su Myat Mon | Minor |  | 8,9,16 is holiday
5 | EMS | UAT | Meeting Minute Edit |  |  | CPM Role တွင် မိမိပါသော Complete Meeting တွင် Status (Finished, On Going) ဖြည့်ထားလျှင် Meeting Minute Edit ပြင်ပြီး Save Change နှိပ်မ၍ ရချင်ပါသည်။ Super Admin Role (Complete Meeting, All Meeting) တွင်ပါ Change ခွင့်ရချင်ပါသည်။ | CHLD | Thiri Sandar Htun |  | JUNE | New | 2024-06-03 | Pass | 2024-06-03 | 2024-06-04 | 1 | Su Myat Mon | Minor
6 | EMS | UAT | Reporting |  |  | Admin Role နဲ့ ဝင်ထားတာကို Reporting Summary မှာ တခြား BU ကိုပါ မြင်နေရပါတယ်။ | CHLD | Sandar Aung |  | JUNE | OutStanding | 2024-06-01 | Pass | 2024-06-03 | 2024-06-17 | 11 | Su Myat Mon | Minor |  | 8,9,16 is holiday
7 | EMS | UAT | Reporting |  |  | Admin Role နဲ့ ဝင်ထားတာကို Reporting Achievement မှာ All ကိုပါ မြင်နေရပါတယ်။ | CHLD | Sandar Aung |  | JUNE | OutStanding | 2024-06-01 | Pass | 2024-06-03 | 2024-06-17 | 11 | Su Myat Mon | Minor |  | 8,9,16 is holiday
8 | EMS | UAT | Reporting |  |  | Reporting ရဲ့ Task မှာ Relaed Dept မဟုတ်တာတွေပါ မြင်နေရပါတယ်။ | CHLD | Sandar Aung |  | JUNE | OutStanding | 2024-06-01 | Pass | 2024-06-03 | 2024-06-17 | 11 | Su Myat Mon | Minor |  | 8,9,16 is holiday
9 | EMS | UAT | User Management |  |  | Super Admin Right နှင့် Super Admin Right ရှိသူအား Right ပြောင်းပေးရန် Edit Buttom မပါပါ။ | CHLD | Khin May Cho |  | JUNE | User Issue | 2024-05-30 | Pass | 2024-06-03 | 2024-06-04 | 1 | Su Myat Mon | Minor
10 | EMS | UAT | User Management |  |  | Roles, Permission အသစ်များ Create လုပ်ပြီး ပြန်ဖျက်ချင်သည့်အခါ Delete Button မပါပါ။ | CHLD | Khin May Cho |  | JUNE | System Upgrade | 2024-06-03 | Pass | 2024-06-03 | 2024-06-17 | 11 | Su Myat Mon | Minor |  | 8,9,16 is holiday
11 | EMS | UAT | Complete Meeting |  |  | Super Admin Role နှင့် Complete Meeting ရှိ Meeting အားလုံးကို Edti လုပ်ခွင့်ရှိရမည်ဖြစ်သော်လည်း Super Admin ကိုယ်တိုင်ရေးထားသော MOM ကိုသာ Edit လုပ်၍ရပြီး အခြားသူများရေးထားသော MOM ကို Edit လုပ်၍မရပါ။ Edit Button မပါပါ။ | CHLD | Khin May Cho |  | JUNE | User Issue | 2024-06-03 | Pass | 2024-06-03 | 2024-06-04 | 1 | Su Myat Mon | Minor
12 | EMS | UAT | Complete & All Meeting |  |  | All Meeting & Complete Meeting များတွင် CPM & Super Admin Role ရထားသူသည် All BU/BR/DIV အတွက် ကြည့်ရင် BU/BR/DIV Filter ထည့်ပြီး ရှာ ကြည့်မှ သာ ဝင်ပြီး meeting Minute တွေ edit လုပ်လို့ရမှာ မို့လို့ BU/BR/DIV Filteထည့်ပေးရန် | CHLD | SYTP |  | JUNE | System Upgrade | 2024-06-03 | Pass | 2024-06-03 | 2024-06-17 | 11 | Su Myat Mon | Minor |  | 8,9,16 is holiday
13 | EMS | UAT | Complete & All Meeting |  |  | All Meeting & Complete Meeting များတွင် CPM & Super Admin Role ရထားသူသည် All Meeting Plan & All complete Meeting များ မမြင်ရပါ Related BU/BR/DIV ကိုသာ မြင်ရပါသည် | CHLD | SYTP |  | JUNE | System Issue | 2024-06-03 | Pass | 2024-06-03 | 2024-06-21 | 15 | Su Myat Mon | Major | the listview of all meeting types | 8,9,16 is holiday
14 | EMS | UAT | Complete & All Meeting |  |  | All Meeting & Complete Meeting များတွင် BU အလိုက် filter ရွေးလို့ ရရန်, List view တွင် BU/BR/Name , Dept Name ပေါ်ပေးရန် | CHLD | SYTP |  | JUNE | System Upgrade | 2024-06-03 | Pass | 2024-06-03 | 2024-06-17 | 11 | Su Myat Mon | Minor |  | 8,9,16 is holiday
15 | EMS | UAT | View |  |  | User Name အောက်တွင် ဖြစ်ဖြစ် ရထားသော Role အား ဖော် ပြပေးရန်။ ဥပမာ User Name ( Admin) | CHLD | SYTP |  | JUNE | System Upgrade | 2024-06-03 | Pass | 2024-06-03 | 2024-06-17 | 11 | Su Myat Mon | Minor |  | 8,9,16 is holiday
16 | EMS | UAT | View |  |  | Plan လုပ်ထားတဲ့ Meeting နှင့် Invite တန်းလုပ်ထားတဲ့ meeting ခွဲ ပြထားတဲ့ color ကို အရောင်ဖျော့ သုံးပေးရန် ( color ကို ပြန် ညွှန်းပေးရန်) ဥပမာ- Hight light color - Plan Meeting | CHLD | SYTP |  | JUNE | Change | 2024-06-03 | Pass | 2024-06-03 | 2024-06-17 | 11 | Su Myat Mon | Minor |  | 8,9,16 is holiday
17 | EMS | UAT | Reporting |  |  | Reporting Summary တွင် BU အလိုက် Filter ရွေးပြီး MOM Report ထုတ်သော်လည်း Filter ရွေးလိုက်သည့် BU MOM အပြင် Other Business ရဲ့ MOM များပါ Report တွင်ကျလာပါသည်။ | CHLD | KMC |  | JUNE | User Issue | 2024-06-04 | Pass | 2024-06-03 | 2024-06-04 | 1 | Su Myat Mon | Minor
18 | EMS | UAT | Internal (Web) |  |  | Attendance Add နေရာတွင် Add PIC ရွေးသောအခါ Department Name မကျလာပဲ တခါတလေ Blank ဖြစ်နေပါသည်၊ တခါတလေ ရပါသည်။ | CHLD | Thiri Sandar Htun |  | JUNE | System Upgrade | 2024-06-01 | Pass | 2024-06-03 | 2024-06-17 | 11 | Su Myat Mon | Minor |  | 8,9,16 is holiday
19 | EMS | UAT | Internal (Web) |  |  | Attendance Add ရာတွင် Add PIC တယောက်တည်းကို ထပ်ရွေး၍ ရနေပါသည်၊ Attendance တွင် နှစ်ခါဝင်နေပါသည်။ | CHLD | Thiri Sandar Htun |  | JUNE | System Upgrade | 2024-06-01 | Pass | 2024-06-03 | 2024-06-17 | 11 | Su Myat Mon | Minor |  | 8,9,16 is holiday
20 | EMS | UAT | Internal (Web) |  |  | Internal Meeting တွင် MOM Pending Status ဖြည့်လျှင် Pending Reason ပါမှ Submit လုပ်၍ရရန်။ Pending Condition ဖြစ်နေသော်လည်း Pending Reason မပါပဲ Submit လုပ်၍ ရနေပါသည်။ | CHLD | Thiri Sandar Htun |  | JUNE | Change | 2024-06-01 | Pass | 2024-06-03 | 2024-06-17 | 11 | Su Myat Mon | Minor |  | 8,9,16 is holiday
21 | EMS | UAT | Meeting Minute |  |  | KPI Meeting Minute တွင် Meeting Minute ရေးပြီးသော်လည်း KPI score မပေးရသေးသောကြောင့် MOM ကို sent မလုပ်ပဲ Save as Draft လုပ်ထားပေမယ့် Status တွင် Draft ဟုမပေါ်ဘဲ On Progress ဟုသာပေါ်နေပါသည်။ | CHLD | Khin May Cho |  | JUNE | User Issue | 2024-06-01 | Pass | 2024-06-03 | 2024-06-04 | 1 | Su Myat Mon | Minor
22 | Core ERP | UAT | Inventory |  |  | Stock card report တွင်ပါသောQty နှင့် Actual Done Qty လွဲနေခြင်း။ | CFD | Phyo Nanda Kyaw | Medium | JUNE | System Issue |  | Pass | 2024-05-31 | 2024-06-05 | 4 | Paing Soe Chit | Minor |  | 2 is holiday
23 | Hi5 F&A | UAT v. 2.6.8 | AR |  | Rescheduled Date Filter | Remind, Repayment, Payment Collect (Reschedule date Filter) စစ်ပေးခြင်း | CFD | CFD | Medium | JUNE | System Upgrade | 2024-06-10 | Pass | 2024-06-10 | 2024-06-15 | 5 |  | Major | Activity ၃ခုအတွက် Scenario အလိုက် date filter များကို due date နဲ့စစ်ထားရသည်
24 | Hi5 F&A | UAT v. 2.6.8 | AR |  | Paid Type, Rescheduled Amount | Calculation for Paid Type , Rescheduled amount of Payment Collect | CFD | CFD | Medium | JUNE | Additional | 2024-06-11 | Pass | 2024-06-11 | 2024-06-14 | 3 |  | Minor
25 | Hi5 F&A | UAT v. 2.6.8 | AR |  | Hi5 Register Payment | Cash/Bank Transfer မှာ Register Payment နှိပ်ပီး Journal choose ပြီး paid တာနဲ့ Core ERP's Payment draft ကျပေးခြင်း | CFD | CFD | High | JUNE | System Upgrade | 2024-06-13 | Pass | 2024-06-13 | 2024-06-13 | 0 |  | Major | Core ERP's invoice မှာ register payment က wizard box အတိုင်း Hi5 မှာ အသစ် ထပ်ထည့်ပေးထားသည်
26 | Hi5 F&A | UAT v. 2.6.8 | AR |  | Repayment (Outstanding) | Repayment (Outstanding) မှာ count calculation ပြင်တွက်ပေးခြင်း | CFD | CFD | Medium | JUNE | Change | 2024-06-10 | Pass | 2024-06-10 | 2024-06-10 | 0 |  | Minor
27 | Hi5 F&A | UAT v. 2.6.8 | AR |  | Legal < AR Collect> | Legal < AR collect> ကို Core ERP's register payment မှာ full or partial payment ရှိရင် "AR Collect" - success ဖြစ်ပေးရန် | CFD | CFD | Medium | JUNE | Change | 2024-06-25 | Pass | 2024-06-25 | 2024-06-26 | 1 |  | Minor
28 | Hi5 F&A | UAT v. 2.6.8 | AR |  | Repossess <AR Clear> | Repossess <AR Clear> လုပ်တဲ့အခါ Repossess မှာပဲ လျော့ပေးပြီး All incomplete မှာ AR ပြန်မတက်ရန် | CFD | CFD | Medium | JUNE | System Issue | 2024-06-26 | Pass | 2024-06-26 | 2024-06-26 | 0 |  | Minor
29 | Mechanic Activity(After Sales) | UAT | E-Learning |  | Disappear data | Job assign is being blank in your recording also. why? | AFS | Cherry Soe |  | JUNE | System Issue | 2024-06-01 | Pass | 2024-06-01 | 2024-06-01 | 0 |  | Minor
30 | Mechanic Activity(After Sales) | UAT | E-Learning |  | Revenue report | Revenue report ထုတ်တဲ့ အခါ machine business မှာ Falseကျနေလို့. | AFS | Cherry Soe |  | JUNE | System Issue | 2024-05-27 | Pass | 2024-05-27 | 2024-06-01 | 4 |  | Minor
31 | Mechanic Activity(After Sales) | UAT | E-Learning |  |  | Disappear detail job information in Share Job of E-learning. | AFS | Cherry Soe |  | JUNE | System Issue | 2024-06-03 | Pass | 2024-06-03 | 2024-06-06 | 3 |  | Minor
32 | Mechanic Activity(After Sales) | UAT | E-Learning |  |  | DIV head က share job ကို အမပြောတဲ့ access right ပေးထားတာတောင် approve မပေါ်သေးလို ပြန်ကြည့်ပေးပါဦးနော်။ | AFS | Cherry Soe |  | JUNE | User Issue | 2024-06-12 | Pass | 2024-06-12 | 2024-06-13 | 1 |  | Minor