## Project Devlopment
Data input : F - CID - CRM - Project Development | [9 empty] | Legend | Recommendations
Target -100%
Financial Year | 2023/2024 |  |  |  | 2024/2025 |  |  |  |  | Calculated KPI Data (Do not change)
Month | Target No. of release according to project timeline | Actual No. of Release project | Achievement |  | Target No. of release according to project timeline | Actual No. of Release project | Achievement |  |  | Your data (White Cells) | Please fill in your data in blank white cells
[10 empty] | 1 | Turnover is conforming with established target (well done and keep improvement)
Apr |  |  |  | 90% | 10 | 10 | 100% | 100% |  | 0.5 | Results are under the established target, but within a tolerance interval. They need to be analyzed and monitored
May |  |  |  | 90% | 9 | 9 | 100% | 100% |  | 0 | Turnover exceeds target limit (Please investigate and take urgent actions)
Jun |  |  |  | 90% | 14 | 14 | 100% | 100% | [5 empty] | Trend
Jul |  |  |  | 90% |  |  |  | 100% |  | 2024/2025 |  | J |  | #VALUE!
Aug |  |  |  | 90% |  |  |  | 100%
Sep |  |  |  | 90% |  |  |  | 100%
Oct |  |  |  | 90% |  |  |  | 100%
Nov |  |  |  | 90% |  |  |  | 100% |  | Action Plan
Dec |  |  |  | 90% |  |  |  | 100% |  | 1-……………………………………………………………………………………………..
Jan |  |  |  | 90% |  |  |  | 100% |  | 2-……………………………………………………………………………………………..
Feb |  |  |  | 90% |  |  |  | 100% |  | 3-……………………………………………………………………………………………..
Mar |  |  |  | 90% |  |  |  | 100% |  | 4-……………………………………………………………………………………………..
YTD |  |  |  |  | 33 | 33 |  |  |  | 5-……………………………………………………………………………………………..
Average |  |  |  |  | 11 | 11 |  |  |  | 6-……………………………………………………………………………………………..
Performance |  |  |  |  | 100% |  |  |  |  | 7-……………………………………………………………………………………………..
KPI Analysis
KPI Definition
BSC Perspective | KPI | Process | Frequency | Definition |  |  |  |  | Objective |  |  | Numerator | Denominator
Finicial | Project Development | TBD | Monthly | [8 empty] | Target No. of release according to project timeline | Actual No. of Release project
KPI Profile
Direction | Unit
Maximize | Percentage

## Apr
No | Month | Business Unit | Participants | Project Name | Function/Module Name(Phase by Phase) | Release Date | PIC Name | Evidence | Remark
1 | APRIL | Aftersales | Moe Thu Han Myat Thazin Aye Kyu Kyu Win Nay Aung Ei Mon Kyaw | Mechanic Activity | UAT Release User Issue Feedback V 1.3.0 Total Counts = 7 - System Ugprade = 5 - Additional = 2 | 2024-04-05 | Myat Thazin Aye | Evidence 1 | UAT
2 | APRIL | Win Finance | Moe Thu Han Aung Paing Soe Wah Wah Moe Moe Thu Han Myat Thazin Aye | Win Finance | Go-Live Release V 2.3.0 (Admin Side), V 2.1.0 (Moible) - Customer App Myanmar Language - Credit assessment pass by CS Head report - Credit assessment fail by CS Head report - Request approve by Finance Report | 2024-04-01 | Myat Thazin Aye | Evidence 2 | Go-Live
3 | APRIL | Win Finance | Moe Thu Han Aung Paing Soe Wah Wah Moe Moe Thu Han Myat Thazin Aye | Win Finance | Go-Live Release V 2.3.1 (Admin Side), V 2.1.1 (Moible) - Version force fpdate - Manual customer creation - Dashboard - Change theme color & UI - Photo upload CL Inquiry - Rate us & feedbacks - Share app | 2024-04-25 | Myat Thazin Aye | Evidence 3 | Go-Live
4 | APRIL | CHLD | Aye Chan Myae May Phyo Thu Kyu Kyu Win | EDMS | Release EDMS Phase_1 Version 1.2.1 Total Counts = 8 - Additional = 4 - Changed = 2 - System Issue = 2 | 2024-04-01 | Aye Chan Myae | Evidence 4 | UAT
5 | APRIL | CHLD | Aye Chan Myae May Phyo Thu Kyu Kyu Win | EDMS | Release EDMS Phase_1 Version 1.2.2 Total Count = 3 - Additional =2 - Changed = 1 | 2024-04-03 | Aye Chan Myae | Evidence 5 | UAT
6 | APRIL | After Sales | Eaint Ei Ei Poe Eain Lin Latt Cham Nyein Ko Ei Mon | Spare Part Salesman | Release SparePart Salesman Total Count = 9 - System Issue = 8 - Changed = 1 | 2024-04-11 | Aye Chan Myae | Evidence 6 | UAT
7 | APRIL | CFD | Moe Thu Han Khin Zar Htwe Zaw Thu Htet Ame Nyein Chan Kyaw Kaung Khant Tin Paing Soe Chit | Core ERP | Release Golive Issue Feedback System Issue = 4 counts | 2024-04-03 | Ame Nyein Chan Kyaw .Kaung Khant Tin Paing Soe Chit | Evidence 7 | Go-Live
8 | APRIL | CFD | Moe Thu Han Khin Zar Htwe Zaw Thu Htet Ame Nyein Chan Kyaw Kaung Khant Tin Paing Soe Chit | Core ERP | Release Golive Issue Feedback System Issue = 1 counts | 2024-04-05 | Ame Nyein Chan Kyaw .Kaung Khant Tin Paing Soe Chit | Evidence 8 | Go-Live
9 | APRIL | CAM | Moe Thu Han Thin Ei San Wah Wah Moe Su Myat Mon | AMS | Go-Live Release (Mobile) -Asset Go See -Fleet Go See | 2024-04-02 | Su Myat Mon | Evidence 9 | Go-Live
10 | APRIL | CHLD | Moe Thu Han Aung Kaung Moe Aye Naung Thu Su Myat Mon | TIS | UAT Release User Issue Feedback V 2.4.1 Total Count = 2 -Changes Requirement =2 | 2024-04-24 | Su Myat Mon | Evidence 10 | UAT

## May
No | Month | Business Unit | Participants | Project Name | Function/Module Name(Phase by Phase) | Release Date | PIC Name | Evidence | Remark
1 | MAY | Aftersales | Moe Thu Han Myat Thazin Aye Nay Aung Ei Mon Kyaw | Mechanic Activity | UAT Release User Issue Feedback V 1.4.0 Total Counts = 13 Additional =6 System Upgrade = 4 New = 2 System Issue =1 | 2024-05-17 | Myat Thazin Aye | Evidence 1 | UAT
2 | MAY | Aftersales | Moe Thu Han Myat Thazin Aye Nay Aung Ei Mon Kyaw | Mechanic Activity | UAT Release User Issue Feedback V 1.4.1 Total Counts = 8 System Upgrade =1 System Issue = 7 | 2024-05-31 | Myat Thazin Aye | Evidence 2 | UAT
3 | MAY | CHLD | Moe Thu Han Aung Kaung Moe Aye Naung Thu Su Myat Mon | TIS | UAT Release V2.5.0 (Web & Mobile) 1. Question Create 2. Assessment Create 3. Assessment Timeline View 4. Superior/HR Assessment Result 5. Reporting • Summary Report • Individual Report • Achievement Detail Report 6. Access Right ( All+ Reporting ) 7. Enrollment filter by Employment Type | 2024-05-29 | Su Myat Mon | Evidence 3 | UAT
4 | MAY | CHLD | Moe Thu Han Htun Myint Win Su Myat Mon | EMS | UAT Release V2.4.0 (Web) 1. Access Right • Employee (All + Reporting) • Admin (All + Reporting) • CPM (All +Reporting) • Super Admin (All + Reporting) 2. Meeting Title Inactive | 2024-05-27 | Su Myat Mon | Evidence 4 | UAT
5 | MAY | CHLD | Moe Thu Han Myat Thazin Aye Moe Thu Khaing Su Myat Mon Thin Ei San Ei Mon Kyaw | Core HR | UAT Release V4.2.0(Odoo) 1. Confirmation Schedule 2. Confirmation Assessment 3. Confirmation Checklist | 2024-05-31 | Su Myat Mon | Evidence 5 | UAT
6 | MAY | CHLD | Moe Thu Han Myat Thazin Aye Moe Thu Khaing Su Myat Mon Thin Ei San Ei Mon Kyaw | Core HR | UAT Release User Issue Feedback Recommendation Request (Mobile) Total Counts = 9 | 2024-05-31 | Su Myat Mon | Evidence 6 | UAT
7 | MAY | CFD | Moe Thu Han Khin Zar Htwe Zaw Thu Htet Ame Nyein Chan Kyaw Kaung Khant Tin Paing Soe Chit Wint Wah Ko | Core ERP | Release Golive Issue Feedback System Issue = 2 counts | 2024-05-14 | Ame Nyein Chan Kyaw Kaung Khant Tin Paing Soe Chit | Evidence 7 | Go-Live
8 | MAY | CHLD | Moe Thu Han Myat Thazin Aye Moe Thu Khaing Su Myat Mon Thin Ei San Ei Mon Kyaw | Core HR | UAT Release V 4.2.0 1. Manpower Planning 2. Vacant Requisition 3. Vacant Fulfillment | 2024-05-24 | Myat Thazin Aye Moe Thu Khaing Su Myat Mon | Evidence 8 | UAT
9 | MAY | CHLD | Moe Thu Han Myat Thazin Aye Moe Thu Khaing Su Myat Mon Thin Ei San Ei Mon Kyaw | Core HR | Go-Live Feedbacks 1. Promotion/Demotion upgrade 2. Disappaer Salary Configure CRUD access right 3. Read only in number of days in leave request 4. Update leave request from 5. Payroall bactch default group by changes 6. Change menu name Employee Loan as Deduction 7. Add multi annaul leave request permission | 2024-05-03 | Myat Thazin Aye Moe Thu Khaing Su Myat Mon | Evidence 9 | Go-Live

## Jun
No | Month | Business Unit | Participants | Project Name | Function/Module Name(Phase by Phase) | Release Date | PIC Name | Evidence | Remark
1 | JUNE | CAM | Moe Thu Han Su Myat Mon Thin Ei San | AMS | UAT Release V3.7.0 (Odoo) 1. Vehicle Reporting (pdf) • Fuel advance • Fuel clear • Fuel claim • Fuel expense summary • Monthly extra fuel amount • Repair Advacne • Repair Clear • Repair Claim • Vehicle Exit Permit • Taxi (bus,motorcycle,3-wheel etc...) Charges 2. Changes Requirement - 4 | 2024-06-13 | Su Myat Mon | JUNE 1 | UAT
2 | JUNE | CAM | Moe Thu Han Su Myat Mon Thin Ei San | AMS | UAT Release V3.7.1 (Odoo) 1. Outstanding - 1 2. System Upgrade -2 | 2024-06-26 | Su Myat Mon | JUNE 2 | UAT
3 | JUNE | CHLD | Moe Thu Han Su Myat Mon Aung Kaung Moe Aye Nhaung Thu | TIS | UAT Release V2.5.1(Web+Mobile) 1. After Training Assessment Draft State | 2024-06-13 | Su Myat Mon | JUNE 3 | UAT
4 | JUNE | CHLD | Moe Thu Han Su Myat Mon Htun Myint Win Aung Kaung Moe | EMS | UAT Release V2.4.1(Web+Mobile) 1.Additional Phase (1+2) • Outstanding -1 • System Upgrde - 7 • Additional - 1 • Change Requirement - 1 2.Phase 2 Access Right Issue Fixed • Outstanding -3 • System Upgrde - 3 • Additional - 7 | 2024-06-17 | Su Myat Mon | JUNE 4 | UAT
5 | JUNE | CFD | Moe Thu Han Zaw Thu Htet Kaung Khant Tin Paing Soe Chit Wint Wah Ko | Core ERP | Release UAT Issue Feedback System Issue = 1 counts | 2024-06-05 | .Kaung Khant Tin Paing Soe Chit | JUNE 5 | UAT
6 | JUNE | CFD | Moe Thu Han Zaw Thu Htet Kaung Khant Tin Paing Soe Chit Wint Wah Ko | Core ERP | Release GO_LIVE Issue Feedback System Issue = 1 counts | 2024-06-03 | .Kaung Khant Tin Paing Soe Chit | JUNE 6 | Go-Live
7 | JUNE | CFD | Ma Moe Thu Han Moe Thu Khaing Zaw Thu Htet Wah Wah Moe | Hi5 F&A | Internal Release Hi5 F&A for refix after UAT Feedback (Backend) 1) Repayment <Reschedule date> 2) Payment <Reschedule date,Exchange date> 3) Repayment, Payment Collect <Outstanding> 4) RV Draft & Register Payment | 2024-06-15 | Moe Thu Khaing | JUNE 7 | UAT
8 | JUNE | CFD | Ma Moe Thu Han Moe Thu Khaing Zaw Thu Htet Wah Wah Moe | Hi5 F&A | Internal Release Hi5 F&A for refix after UAT Feedback (Frontend) 1) Repayment <Reschedule date filter> 2) Payment <Reschedule date filter, exchange rate> | 2024-06-15 | Moe Thu Khaing | JUNE 8 | UAT
9 | JUNE | CFD | Ma Moe Thu Han Moe Thu Khaing Zaw Thu Htet Wah Wah Moe | Hi5 F&A | Internal Release Hi5 F&A for refix after UAT Feedback (Frontend) 1) RV Draft <status, fields for backend form> | 2024-06-17 | Moe Thu Khaing | JUNE 9 | UAT
10 | JUNE | After Sales | Ma Moe Thu Han Myat Thazin Aye Nay Aung Ei Mon Kyaw | Mechanic Actvity | UAT Release E-Learning - Share job information - Disappear job info | 2024-06-06 | Myat Thazin Aye | JUNE 10 | UAT
11 | JUNE | Win Finance | Ma Moe Thu Han Myat Thazin Aye Aung Paing Soe Wah Wah Moe | Win Finance | Go-Live Release (2.1.2) - Remove near me in payment information - Add M Pitesan - Version force update | 2024-06-27 | Myat Thazin Aye | JUNE 11 | Go-Live
12 | JUNE | CHLD | Ma Moe Thu Han Myat Thazin Aye Moe Thu Khaing Su Myat Mon Thin Ei San Wint War Ko Ei Mon Kyaw | Core HRMS | UAT Release Leave DeductionDeduction (Not measure with KPI results) (1) Medical leave with pay (2) Medical leave without pay (3) Parenity leave (4) Maternity leave (5) Leave (6) Absence (7) Not working day deduction | 2024-06-10 | Myat Thazin Aye Moe Thu Khaing Su Myat Mon | JUNE 12 | UAT
13 | JUNE | CHLD | Ma Moe Thu Han Myat Thazin Aye Moe Thu Khaing Su Myat Mon Thin Ei San Wint War Ko Ei Mon Kyaw | Core HRMS | Go-Live Change User Login Password Total Count : 369 | 2024-06-14 | Myat Thazin Aye Moe Thu Khaing Su Myat Mon | JUNE 13 | Go-Live
14 | JUNE | CHLD | Ma Moe Thu Han Myat Thazin Aye Moe Thu Khaing Su Myat Mon Thin Ei San Wint War Ko Ei Mon Kyaw | Core HRMS | Go-Live Release (Feedbacks Fixed) -Leave DeductionDeduction (Not measure with KPI results) (1) Medical leave with pay (2) Medical leave without pay (3) Parenity leave (4) Maternity leave (5) Leave (6) Absence (7) Not working day deduction -Related HR Leave mail link -Leave Request Validation (Half-Day Leave) -Management domain filter (Promo/domo) -Resign & Termination effective date & request date -Fix for Currency (USD/MMK) in current salary report | 2024-06-15 | Myat Thazin Aye Moe Thu Khaing Su Myat Mon | JUNE 14 | Go-Live